## Overview
Stream | Goal | Target | Owner | Notes
Enterprise Pipeline | New ARR | $500K | Phily / Zach
Enterprise Pipeline | Q3 Pipeline | $2.1M | Phily / Zach / BDR
Enterprise Pipeline | Hedge fund logos closed | 3 | Phily / Zach
Enterprise Pipeline | Partnership deals closed | 2 | Phily
Enterprise Pipeline | BDR hired | 1 | Phily / Zach | Start June 1
Enterprise Pipeline | BDR weekly outbound | 500 calls/emails/LIs | BDR | From mid-June
Enterprise Pipeline | Zach weekly outbound | 200 emails/LIs | Zach
Enterprise Pipeline | Founder weekly outbound (each) | 100 | P / J / G
Mega Launch | Social impressions in 48 hrs | 5M | Zach + Phily
Mega Launch | Virality coefficient | K ≥ 0.8 by week 2 | Zach
Mega Launch | Waitlist signups pre-launch | 10,000 | Zach + Olga
Mega Launch | Researchers posting in 48 hrs | 30+ across 4 domains | Zach
Mega Launch | Pipeline generated from inbound | $300K+ | BDR + Zach
Mega Launch | Product Hunt rank | #1 or #2 | Zach
Community | Net adds by Sep | 5,000+ | Zach | 30%+ from launch + hackathons
SEO | High-quality articles in 12 wks | 18 | Zach + agents

## Q2 Calendar
Month | Week | Stream | Activity | Owner | Status | Priority | Deliverable | Notes
May 2026 | W1 | Enterprise Pipeline | Final-round BDR candidates (3+) | Phily + Zach | Active | P0 | Offer out by W3
May 2026 | W1 | Foundation | Onboard Simon (web dev) — replace Miroslav | Jason | Active | P0 | Unblocker
May 2026 | W1-W2 | Enterprise Pipeline | Sales tech stack procurement: Alta, Clay, Zoom, Fathom, Apollo, Sales Nav, Nooks | Zach + Greg | Active | P0 | All tools live by May W4
May 2026 | W1-W2 | Mega Launch | Vision for program — what researchers get | Zach + Phily | Active | P0 | Approved doc | Verified research, tier-1 advisory board, search page anchor, waitlist
May 2026 | W1-W2 | Mega Launch | Top 50 researchers list per domain | Zach | Active | P0 | List in CRM | 4 domains
May 2026 | W1-W2 | Mega Launch | Validator outreach wave 1 | Phily + Zach | Active | P0
May 2026 | W1-W2 | SEO | Yoni keyword research kickoff | Yoni + Zach | Active | P0 | Unblocks content
May 2026 | W1 onwards | Community | Founder posting cadence (Jason 1×/wk, Phily 1×/wk) | Jason + Phily | Ongoing | P1 | Lock cadence
May 2026 | W1 onwards | Enterprise Pipeline | Founder outbound P/J/G 100 each per week | Phily + Jason + Greg | Ongoing | P0 | CRM logged
May 2026 | W1 onwards | Enterprise Pipeline | Zach outbound 200 emails/LIs per week | Zach | Ongoing | P0 | CRM logged
May 2026 | W2 | Enterprise Pipeline | ICP one-pager (US HFs + multi-strats first 90 days) | Zach + Phily | Active | P0 | Approved doc
May 2026 | W2 | Mega Launch | Define 4 agent use cases (finance/bio/economics/pharma) | Jason + Zach | Active | P0 | Doc
May 2026 | W2 | Mega Launch | Build researcher personas | Zach | Active | P1
May 2026 | W2 | Foundation | Design specs for Simon | Olga | Active | P0 | Required before Simon ramps
May 2026 | W2 | Mega Launch | Decide PR channel (TechCrunch / Sifted / The Information) | Phily | Active | P0 | Decision
May 2026 | W2-W3 | Enterprise Pipeline | US HF/FS account list (250-500 with role names) | Zach | Active | P0 | List in CRM
May 2026 | W2-W3 | Enterprise Pipeline | Competitor doc (Hex, Cursor, Jupyter, Databricks, build-your-own) | Zach | Active | P0 | Living doc
May 2026 | W2-W3 | Community | Zerve gallery filters (notebooks / reports / research) | Olga | Active | P0
May 2026 | W2-W4 | SEO | 15-20 launch-window content pieces in production | Zach + agents | Active | P0 | Most live by launch
May 2026 | W3 | Enterprise Pipeline | Battlecards + positioning per competitor | Zach | Active | P0 | Sales-ready
May 2026 | W3 | Mega Launch | STEPPS mechanics: waitlist referral + invite badges | Olga | Active | P0 | Live by T-8
May 2026 | W3 | Events & Hackathons | Eagle Alpha hackathon (quant) — May 19 | Zach | Confirmed | P0 | Run + follow-up
May 2026 | W3-W4 | Enterprise Pipeline | 3 outbound sequences (cold / warm-back / Eagle Alpha follow-up) | Zach (Phily review) | Active | P0 | Live in Salesloft
May 2026 | W3-W4 | Enterprise Pipeline | Sales enablement pack v1 (quant 1-pager, enterprise data 1-pager, demo deck) | Zach + Phily | Active | P0 | Versioned
May 2026 | W3-W4 | Enterprise Pipeline | Customer case studies × 2 (ITV / S&P / Algolia / BBC / Cubic) | Zach + Phily | Active | P0 | Published
May 2026 | W3-W4 | Mega Launch | Confirm 1-2 researchers per domain who will publish | Phily + Zach | Active | P0 | Signed
May 2026 | W3-W4 | Mega Launch | Brief each academic on the research piece | Zach | Active | P0 | Briefs sent
May 2026 | W3-W4 | Mega Launch | Identify + confirm 10-20 early access users | Zach | Active | P0 | List + outreach | Technical, complex problems
May 2026 | W3-W4 | Mega Launch | Validator outreach wave 2 | Phily + Zach | Active | P0
May 2026 | W3-W4 | Mega Launch | Influencer identification + early outreach | Zach | Active | P0 |  | Eloqwnt video, Stephen Kinsella, others
May 2026 | W3-W4 | Mega Launch | Promote waitlist for self-evolve agent pre-launch | Zach + Olga | Active | P0
May 2026 | W3-W4 | Mega Launch | Website changes for self-evolving agent (new pages, home, pricing) | Olga + Simon | Active | P0 | Live by W4
May 2026 | W3-W4 | Mega Launch | Promotional offer for launch (48 hrs unlimited credits?) | Phily + Zach | Active | P0 | Decision
May 2026 | W3-W4 | Features | Data Discovery + Jira/Asana/Slack workflow integrations | Olga + Zach | Active | P1 | Tier 2 launch | One LinkedIn post + one blog
May 2026 | W3-W4 | Community | Separate research publications page on website (citable, DOI) | Olga | Active | P0 | Live
May 2026 | W3-W4 | Community | Onboarding email revamp (consider agentifying) | Olga + Zach | Active | P1 |  | Can slip to June
May 2026 | W3-W4 | SEO | Agent-generated blog content pilot | Jason + Zach | Active | P1 | Pilot live | Story-in-itself
May 2026 | W3-W4 | Features | Hearst customer story video | Zach | Active | P2 | Tier 3 launch
May 2026 | W4 | Enterprise Pipeline | BDR onboarding plan (week 1/4/8/12 ramp targets) | Zach | Active | P0 | Doc + week-1 schedule
May 2026 | W4 | Enterprise Pipeline | BDR comp structure (~$75K base + $35K OTE, SQO-weighted) | Greg + Phily + Zach | Active | P0 | Signed offer
May 2026 | W4 | Events & Hackathons | Conference pipeline — book 3 events June→Sep | Zach | Open | P0 | 3 events booked | Gap to close
May 2026 | W4 | Mega Launch | Lock 6 tier-1 validators + 12 tier-2 | Zach + Phily | Active | P0 | All confirmed
May 2026 | W4 | Foundation | Update product pages with consistent design | Olga + Simon | Active | P1 | Pre-launch polish
June 2026 | W1 | Enterprise Pipeline | BDR day 1 — product training, ICP, tools, shadowing | Zach + BDR | Planned | P0 |  | Tools live before day 1
June 2026 | W1-W2 | Enterprise Pipeline | BDR sequences live by W2 | BDR | Planned | P0 | Outbound running
June 2026 | W1-W2 | Mega Launch | Press embargo briefings | Phily + PR partner | Planned | P0
June 2026 | W1-W2 | Mega Launch | Podcast bookings for launch window | Zach | Planned | P0
June 2026 | W1-W2 | Mega Launch | Define use cases / scripts / channels for early access cohort | Zach | Planned | P0
June 2026 | W1-W2 | Events & Hackathons | HackerEarth hackathon (running) | Zach | Confirmed | P0 |  | Confirmed
June 2026 | W1 onwards | SEO | Sustained content drumbeat ≥2 pieces/week | Zach + agents | Ongoing | P1 | Compounds
June 2026 | W2 | Mega Launch | Final QA of all assets | Zach + Olga | Planned | P0
June 2026 | W2 | Mega Launch | Launch-day comms locked (PH/HN scheduled, validator posts pre-written, embargoes out) | Zach | Planned | P0
June 2026 | W2 | Mega Launch | Influencer wave warmed | Zach | Planned | P0
June 2026 | W2 | Mega Launch | Channel-by-launch-type matrix locked | Zach | Planned | P0
June 2026 | W2 | Community | Public notebook embeds + 'Built with Zerve' badge | Olga | Planned | P1 | Live
June 2026 | W2 | Features | Pricing changes (tied to mega launch) | Phily + Zach | Planned | P1 | Tier 2 launch
June 2026 | W3 (Tue June 16) | Mega Launch | LAUNCH DAY: Product Hunt + HN + Reddit + Devhunt + Peerlist + Indie Hackers + validator cascade + press live + newsletters + Eloqwnt video + Kinsella post | Zach + everyone | Planned | P0 | Launch executed
June 2026 | W3 | Events & Hackathons | Future Alpha quant hackathon (around launch) | Zach | Confirmed | P0 | Run + amplify
June 2026 | W3 | Features | Cubic customer story video | Zach | Active | P2 | Tier 3 launch
June 2026 | W2 onwards | Enterprise Pipeline | BDR target: 500 weekly touches | BDR | Ongoing | P0 | Salesloft dashboard
June 2026 | W2 onwards | Enterprise Pipeline | Weekly pipe-gen review (Mon) + call coaching (Wed) | Zach + BDR | Ongoing | P0 | Recurring
June 2026 | Ongoing | Enterprise Pipeline | Quant flagship deal — accelerate to close | Phily + Zach | Active | P0 | Logo announcement
June 2026 | Ongoing | Enterprise Pipeline | BDR + Zach split Eagle Alpha hackathon follow-up | BDR + Zach | Ongoing | P0 |  | Long-tail vs strategic top accounts
June 2026 | W4 | Mega Launch | Launch retro + KR readouts (impressions, K-factor, waitlist→active) | Zach | Planned | P0 | Retro doc
July 2026 | W1-W2 | Mega Launch | Validator wave 2 amplification | Zach | Planned | P1
July 2026 | W1-W2 | Enterprise Pipeline | Inbound triage from launch (BDR + Zach split demos) | BDR + Zach | Planned | P0
July 2026 | W2 | Features | Canal+ customer story video | Zach | Active | P2 | Tier 3 launch
July 2026 | W2-W3 | Features | Model Registry + Reports/Charts polish + Citation enablement (Themed batch 3) | Olga + Zach | Planned | P1 | Tier 2 launch
July 2026 | W2 | Community | Citation enablement on Zerve outputs | Olga | Planned | P1
July 2026 | Ongoing | SEO | Backlink push via academic preprints | Zach | Ongoing | P1 | Highest-DA links available
July 2026 | W2 | SEO | Elicit-alternative SEO page | Zach | Planned | P1 | Pre-positions Q3 partnership
July 2026 | W3-W4 | Partnerships | Elicit term sheet prepped (Day-1 Q3 ship) | Phily + Zach | Planned | P0 | Term sheet
July 2026 | W3-W4 | Foundation | Pipeline-by-source dashboard (BDR / hackathon / founder-led / inbound) for deck v5 | Zach | Planned | P0 | Slide-ready
July 2026 | W3-W4 | Foundation | Series A deck v5 cleanup (slide 10 tearsheet, slide 2 citations, logo render) | Zach + Phily | Planned | P0 | Investor-ready
July 2026 | W3-W4 | Foundation | Mid-quarter narrative refresh — what's the story? | Zach + Phily + Jason | Planned | P0 | Lock September pitch
July 2026 | Ongoing | Enterprise Pipeline | BDR sustains ≥30 meetings/month, ≥5 SQOs/month | BDR | Ongoing | P0 | Dashboard
July 2026 | Possible | Events & Hackathons | Neudata London Summit (decision) | Zach | Open | P1 |  | Considering
July 2026 | Ongoing | Foundation | Diligence pack assembly (metrics, contracts, churn, cohorts) | Greg + Zach | Active | P0
August 2026 | Ongoing | Enterprise Pipeline | Close 3rd hedge fund logo | Phily + Zach | Active | P0 | Signed
August 2026 | Ongoing | Enterprise Pipeline | Q3 pipeline reaches $2.1M | All | Active | P0 | Reported in deck
August 2026 | Ongoing | Enterprise Pipeline | 2 partnership deals signed | Phily | Active | P0 | Announcements
August 2026 | Ongoing | Partnerships | Identify 3-5 mid-size DB/data partner candidates beyond Eagle Alpha/Ravenpack/Ocient/KX | Phily + Zach | Active | P1 | Shortlist | NOT Snowflake/Databricks
August 2026 | W4 | Enterprise Pipeline | BDR 90-day review — adjust ICP if conversion poor | Zach + Phily | Planned | P1 | Decision
August 2026 | Ongoing | SEO | Continued ≥2 pieces/week + ICP-targeted content | Zach + agents | Ongoing | P1
August 2026 | Ongoing | Foundation | Series A close prep — final docs, references, customer calls | Phily + Greg + Zach | Active | P0 | Close-ready

## Mega Launch
A ¦ Launch Goals
Metric | Target | Owner
Social impressions in 48 hrs | 5M | Zach + Phily
Virality coefficient | K ≥ 0.8 by week 2 | Zach
Waitlist signups pre-launch | 10,000 | Zach + Olga
Researchers posting in 48 hrs | 30+ across 4 domains (finance, bio, economics, pharma) | Zach
Pipeline generated from inbound | $300K+ | BDR + Zach
Product Hunt rank | #1 or #2 | Zach
B ¦ T-Anchored Workback (T+0 = Tue June 16, 2026)
Phase | Window | Focus | Key Activities | Owner
T-12 to T-8 | May W1-W2 | Foundation | Vision doc, top-50 researcher list, validator outreach wave 1, 4 agent use cases defined, Yoni keyword research, content production starts, STEPPS mechanics shipped, PR channel decided | Zach + Phily + Jason + Olga
T-8 to T-4 | May W3 – June W1 | Build pressure | Confirm 1-2 researchers per domain, brief academics, identify 10-20 early access users, press embargo briefings, podcast bookings, validator wave 2, hackathon #1 (Eagle Alpha May 19), waitlist promotion, influencer outreach (Eloqwnt, Kinsella), website changes shipped, promotional offer agreed | Zach + Phily + Olga + Simon
T-4 to T-0 | June W2 | Lock down | Final QA, launch-day comms locked, PH/HN scheduled, influencer wave warmed, channel matrix locked | Zach + Olga
T+0 | Tue June 16 | Execute | PH, HN, Reddit (r/MachineLearning, r/datascience, r/quant, r/genomics), Devhunt, Peerlist, Indie Hackers, validator post cascade, press live (TC + Sifted + stretch), newsletters (Ben's Bites, TLDR, Import AI), Eloqwnt video, Kinsella post, Future Alpha hackathon kickoff | Everyone
T+1 to T+4 | June W4 – July W3 | Compound | Launch retro, KR readouts, validator wave 2 amplification, mid-quarter narrative refresh, inbound triage, agent-generated blog pilot | Zach + Phily
C ¦ Channel-by-Launch-Type Matrix
Launch Type | Primary Channels
Validated research publications | LinkedIn (validator-led), X, academic Twitter, newsletters (Import AI)
Early access cohort showcase | Devpost, Peerlist, Indie Hackers, Reddit r/MachineLearning
General launch | Product Hunt, Hacker News, Devhunt
PR | TechCrunch, Sifted, The Information warm-up
Hackathon-tied | Future Alpha, Eagle Alpha follow-up

## Enterprise Pipeline & BDR
A ¦ Outbound Targets
Channel | Target | Cadence | Owner
BDR outbound | 500 calls/emails/LIs per week | From mid-June | BDR
Zach outbound | 200 emails/LIs per week | Ongoing from May W1 | Zach
Phily outbound | 100 emails/LIs per week | Ongoing from May W1 | Phily
Jason outbound | 100 emails/LIs per week | Ongoing from May W1 | Jason
Greg outbound | 100 emails/LIs per week | Ongoing from May W1 | Greg
B ¦ BDR Ramp Targets
Period | Activity Target | Outcome Target
Week 1 (June W1) | Onboarding, product training, shadowing | Tools live, ICP understood
Weeks 2-4 (June) | Sequences live; 250 touches/wk ramping to 500 | 20-30 meetings booked in June
Month 2 (July) | 500 touches/wk sustained | ≥30 meetings booked, ≥5 SQOs
Month 3 (August) | 500 touches/wk sustained | ≥30 meetings booked, ≥5 SQOs, first SQO closed/late-stage
C ¦ ICP — First 90 Days
• US-based
• Hedge funds + multi-strats only
• No prop trading, family offices, or non-US HFs in first 90 days
• Re-evaluate at month 3
D ¦ Sales Tech Stack
Tool | Purpose | Status
Alta | (TBC primary use) | Procuring May W1-W2
Clay | Account list enrichment | Procuring May W1-W2
Zoom | Meetings | Live
Fathom | Call recording / coaching | Procuring May W1-W2
Apollo | Data | Procuring May W1-W2
LinkedIn Sales Navigator | Prospecting | Procuring May W1-W2
Nooks | Parallel dialler | Procuring May W1-W2
HubSpot (existing) | CRM | Live, needs cleanup
E ¦ BDR Documentation Deliverables
Document | Owner | Deadline
ICP one-pager | Zach + Phily | May W2
Account list (250-500 with role names) | Zach | May W2-W3
Sales tech stack provisioned | Zach + Greg | May W4
Competitor doc | Zach | May W2-W3
Battlecards & positioning | Zach | May W3
Onboarding plan + week-1 schedule | Zach | May W4
3 outbound sequences (cold / warm-back / Eagle Alpha) | Zach | May W3-W4
Sales enablement pack v1 (1-pagers + demo deck) | Zach + Phily | May W3-W4
F ¦ BDR Comp Structure
Base salary | ~$75K
OTE (variable) | $35K (SQO-weighted accelerators above quota)
Sign-off | Greg by May W2

## Implications
Function | Activity | Trigger | Owner | Window
WEB DEV (Olga + Simon)
Web dev | Onboard Simon (replace Miroslav) | Foundation | Jason | May W1
Web dev | Self-evolving agent landing page + waitlist flow | Mega Launch | Olga + Simon | May W3
Web dev | New product pages, home page update, pricing pages | Mega Launch | Olga + Simon | May W4
Web dev | STEPPS mechanics (referral + invite badges) | Mega Launch | Olga | May W3-W4
Web dev | Research publications page | Community | Olga | May W3-W4
Web dev | Public notebook embeds + 'Built with Zerve' badge | Community | Olga | June W2
Web dev | Event landing pages (Eagle Alpha, Future Alpha, Neudata) | Events | Olga + Simon | As needed
Web dev | Conference + partner pages updated post-launch | Multiple | Olga + Simon | Rolling
Web dev | Citation enablement | Community | Olga | July
DESIGN (Olga)
Design | Design specs for Simon | Foundation | Olga | May W2 (blocking)
Design | Customer story video assets (Hearst, Cubic, Canal+) | Features | Olga | May–July
Design | Mega launch creative (PH assets, social cards, validator templates) | Mega Launch | Olga | May W4 onwards
Design | Sales enablement pack design | Enterprise Pipeline | Olga | May W3-W4
CONTENT PRODUCTION (Zach + agents)
Content | 15-20 launch-window pieces | Mega Launch + SEO | Zach + agents | May W2-W4
Content | BDR enablement (battlecards, ICP one-pager, sequences) | Enterprise Pipeline | Zach | May
Content | Customer case studies × 2 | Enterprise Pipeline | Zach + Phily | May W3-W4
Content | Series A deck v5 | Foundation | Zach + Phily | July W3-W4
Content | Sustained content cadence ≥2/week | SEO | Zach + agents | June–August
FOUNDER CONTENT CADENCE
Founder cadence | Jason 1× LinkedIn post per week | Community | Jason | May onwards
Founder cadence | Phily 1× LinkedIn post per week | Community | Phily | May onwards
Founder cadence | Phily mid-quarter narrative refresh | Foundation | Phily | July W4
FOUNDATION / OPS
Foundation | Onboard Simon | Foundation | Jason | May W1
Foundation | BDR onboarding + tooling live | Enterprise Pipeline | Zach | June 1
Foundation | Finance + ops diligence prep (data room skeleton) | Foundation | Greg | May–June
Foundation | Diligence pack assembly (metrics, contracts, churn, cohorts) | Foundation | Greg + Zach | July
Foundation | Series A deck v5 final | Foundation | Zach + Phily | July W3-W4